# I-WALLET: 39-Day Team Build Plan & Task Breakdown

Track: Sui Overflow 2026 — Agentic Web Track
Deadline: June 21, 2026

# Overview

The revised I-Wallet execution plan compresses the original 12-week roadmap into an aggressive 39-day sprint focused on delivering a fully functional autonomous AI wallet infrastructure before the submission deadline.

Key organizational updates include:

- The Sui Solution Engineer now owns the off-chain Trojan Horse Agent Daemon.

- The Project Manager owns the final demo narrative and submission coordination.

- The Dev Advocate begins documentation during Phase 2 instead of the final sprint.

# Master Timeline (39 Days)

| Phase | Dates | Primary Goal |
| --- | --- | --- |
| Phase 1 — Identity Sprint | May 13 – May 24 | ZK circuit implementation and AgentObject Move logic on Sui Testnet |
| Phase 2 — Vault Sprint | May 25 – June 4 | Pull-based execution mechanism and MandateObject enforcement |
| Phase 3 — Ecosystem Sprint | June 5 – June 15 | DeepBook integration, Walrus audit trail, and Trojan Horse feature completion |
| Phase 4 — Submission Sprint | June 16 – June 21 | Final polish, pitch video, testing, and submission |

Critical Lock Date: June 13, 2026

# Team Task Breakdown

# 1. Protocol Engineer (George-Goldman)

The Protocol Engineer owns the cryptographic foundation of the protocol, including the ZK circuit, Groth16 prover system, and developer CLI tooling.

## Phase 1 — Identity Sprint (May 13 – May 24)

- Design the AgentIdentityProof circuit.

- Run trusted setup ceremonies.

- Export the verification key for Move contract integration.

- Build the initial prover binary.

## Phase 2 — Vault Sprint (May 25 – June 4)

- Validate proof outputs against expected public signals.

- Coordinate with the Sui Solution Engineer on proof byte ABI formatting.

## Phase 3 — Ecosystem Sprint (June 5 – June 15)

- Build CLI tooling with:

  - fund

  - trade

  - status

- Package CLI as an installable binary.

## Phase 4 — Submission Sprint (June 16 – June 21)

- Resolve final CLI bugs.

- Support daemon integration and ZK execution flow wiring.

# 2. Sui Solution Engineer

The Sui Solution Engineer owns all Move smart contract logic and the off-chain Trojan Horse Agent Daemon.

## Phase 1 — Identity Sprint (May 13 – May 24)

- Design:

  - AgentObject

  - MandateObject

- Implement TTO receive logic.

- Configure shared object storage patterns.

## Phase 2 — Vault Sprint (May 25 – June 4)

- Implement:

  - Shared storage object

  - Pull-based fund execution mechanism

- Embed verification key inside verifier.move.

## Phase 3 — Ecosystem Sprint (June 5 – June 15)

- Implement DeepBook V3 CPI execution flow.

- Build the Trojan Horse Agent Daemon:

  - Integrates with the Protocol Engineer CLI/Prover

  - Executes automated trades from market signals

  - Generates and submits Groth16 proofs

Hard Requirement: Fully functional by June 13.

## Phase 4 — Submission Sprint (June 16 – June 21)

- Freeze devnet contracts.

- Support full end-to-end demo execution.

# 3. Frontend Engineer

The Frontend Engineer owns the dashboard UI and public-facing web platform.

## Phase 1 — Identity Sprint (May 13 – May 24)

- Set up Next.js repository.

- Integrate Mysten dApp Kit.

- Configure Sui wallet connectivity.

## Phase 2 — Vault Sprint (May 25 – June 4)

- Build:

  - Agent Dashboard shell

  - “Fund Agent” TTO panel

## Phase 3 — Ecosystem Sprint (June 5 – June 15)

- Build:

  - Mandate creation form

  - Proof history log

  - Live Trade Monitor

- Consume daemon event feeds.

## Phase 4 — Submission Sprint (June 16 – June 21)

- Final UI/UX polish.

- Deploy production build to Vercel.

# 4. Dev Advocate / Community Lead

The Dev Advocate owns ecosystem visibility, documentation, and storytelling.

## Phase 1 — Identity Sprint (May 13 – May 24)

- Write the I-Wallet one-pager.

- Begin Twitter/X awareness campaign around:

  - “No Private Key Architecture”

  - Agentic execution infrastructure

## Phase 2 — Vault Sprint (May 25 – June 4)

- Launch GitBook/docs drafting.

- Publish architecture explainer thread.

## Phase 3 — Ecosystem Sprint (June 5 – June 15)

- Finalize CLI documentation.

- Draft:

  - 3-minute pitch script

  - Sui Overflow submission copy

## Phase 4 — Submission Sprint (June 16 – June 21)

- Record and edit final demo video.

- Compile and submit final package to the Overflow portal.

# 5. Project Manager

The Project Manager owns delivery execution, coordination, and final submission management.

## Phase 1 — Identity Sprint (May 13 – May 24)

- Configure Notion tracking system.

- Define sprint completion criteria.

## Phase 2 — Vault Sprint (May 25 – June 4)

- Track ABI coordination between:

  - Protocol Engineer

  - Sui Solution Engineer

- Monitor documentation progress.

## Phase 3 — Ecosystem Sprint (June 5 – June 15)

- Enforce the June 13 Functional Lock milestone.

- Coordinate internal dry-run testing.

## Phase 4 — Submission Sprint (June 16 – June 21)

- Run final pre-flight checklist.

- Supervise demo recording session.

- Execute final submission on June 21.

# Final Milestone: Autonomous Trading Agent Test

## (June 13 – June 18)

The final demonstration validates complete autonomous execution without human intervention.

## Demo Flow

- Sui Solution Engineer deploys contracts to devnet.

- Protocol Engineer and Sui Solution Engineer configure:

  - witness files

  - mandate ID

  - daemon runtime

- Frontend Engineer verifies dashboard tracking.

- Dev Advocate begins screen recording.

- Project Manager validates:

  - active mandate

  - funded balance

- Agent Daemon:

  - receives market signal

  - generates Groth16 proof

  - submits trade to devnet

- DeepBook trade executes successfully.

- Dashboard updates in real time.

- Settlement returns proceeds to the AgentObject..